## Tab
Project tracking - Team GNLG2 - 29/10/2021
Members
|  | CM | Chaymae MAHDI
|  | OS | Oussama SAMIA
|  | PDM | Prince Divin MACKPAYEN
|  | ICC | Ivo COSTA CUHA
|  | LB | Lahcene BOUSADIA
| Tasks |  |  |  | This list may be updated
|  | GM | General Management
|  | GM.MET | Meeting
|  | WR | Workbook Redaction
|  | PT | Project Tracking
|  | PC | Project Conception
|  | DEV | Development
|  | DEV.MET | Development metting
|  | L | Learning about
|  | L.GF | Learning about GEDCOM files
|  | L.DB | Learning about DB
|  | O | Other
Project follow-up
|  | Date | Who | What | Cost (d) | Feedback
|  | 2021-10-22 | CM | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-22 | PDM | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-22 | LB | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-22 | ICC | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-22 | OS | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-22 | CM | GM.MET | 0.3 | Team metting to update the team with the software that the project will use and make sure everyone can install it
|  | 2021-10-22 | PDM | GM.MET | 0.3 | Team metting to update the team with the software that the project will use and make sure everyone can install it
|  | 2021-10-22 | LB | GM.MET | 0.3 | Team metting to update the team with the software that the project will use and make sure everyone can install it
|  | 2021-10-22 | ICC | GM.MET | 0.3 | Team metting to update the team with the software that the project will use and make sure everyone can install it
|  | 2021-10-22 | OS | GM.MET | 0.3 | Team metting to update the team with the software that the project will use and make sure everyone can install it
|  | 2021-10-22 | CM | WR | 0.4 | 1st version of the workbook
|  | 2021-10-22 | PDM | WR | 0.4 | 1st version of the workbook
|  | 2021-10-22 | LB | WR | 0.4 | 1st version of the workbook
|  | 2021-10-22 | ICC | WR | 0.4 | 1st version of the workbook
|  | 2021-10-22 | OS | WR | 0.4 | 1st version of the workbook
|  | 2021-10-27 | CM | GM.MET | 0.3 | Meeting with M. Oudot
|  | 2021-10-27 | PDM | GM.MET | 0.3 | Meeting with M. Oudot
|  | 2021-10-27 | LB | GM.MET | 0.3 | Meeting with M. Oudot
|  | 2021-10-27 | OS | GM.MET | 0.3 | Meeting with M. Oudot
|  | 2021-10-27 | ICC | GM.MET | 0.3 | Sick
|  | 2021-10-28 | CM | PC | 0.45 | Acquaintance with source code
|  | 2021-10-28 | OS | PC | 0.45 | Acquaintance with source code
|  | 2021-10-28 | PDM | PC | 0.45 | Acquaintance with source code
|  | 2021-10-28 | ICC | PC | 0.45 | Acquaintance with source code
|  | 2021-10-28 | LB | PC | 0.45 | Acquaintance with source code
|  | 2021-10-29 | CM | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-29 | PDM | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-29 | LB | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-29 | ICC | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-29 | OS | GM.MET | 0.1 | Meeting with the client (M. Renevier)
|  | 2021-10-28 | CM | PC | 0.5 | Acquaintance with current DB
|  | 2021-10-28 | OS | PC | 0.5 | Acquaintance with current DB
|  | 2021-10-28 | PDM | PC | 0.5 | Acquaintance with current DB
|  | 2021-10-28 | ICC | PC | 0.5 | Acquaintance with current DB
|  | 2021-10-28 | LB | PC | 0.5 | Acquaintance with current DB
|  | 2021-10-29 | CM | WR | 0.4 | 2nd workbook version
|  | 2021-10-29 | PDM | WR | 0.4 | 2nd workbook version
|  | 2021-10-29 | ICC | WR | 0.45 | 2nd workbook version
|  | 2021-10-29 | OS | WR | 0.4 | 2nd workbook version
|  | 2021-10-29 | LB | WR | 0.4 | 2nd workbook version
|  | 2021-10-29 | LB | PT | 0.25 | Project tracking redaction
|  | 2021-11-01 | ICC | WR | 0.5 | 3rd workbook version (layout)
|  | 2021-11-02 | OS | PC | 1 | Current code analysis
|  | 2021-11-02 | LB | PC | 0.8 | Current code analysis
|  | 2021-11-02 | PDM | PC | 1 | Current code analysis
|  | 2021-11-03 | CM | GM.MET | 0.1 | Sick
|  | 2021-11-03 | PDM | GM.MET | 0.1 | Meeting with M. Oudot
|  | 2021-11-03 | LB | GM.MET | 0.1 | Meeting with M. Oudot
|  | 2021-11-03 | OS | GM.MET | 0.1 | Meeting with M. Oudot
|  | 2021-11-03 | ICC | GM.MET | 0.1 | Meeting with M. Oudot
|  | 2021-11-03 | LB | WR | 0.3 | "expoactes" documentation analysis
|  | 2021-11-03 | OS | WR | 0.3 | "expoactes" documentation analysis
|  | 2021-11-03 | PDM | WR | 0.3 | "expoactes" documentation analysis
|  | 2021-11-03 | CM | WR | 0.3 | "expoactes" documentation analysis
|  | 2021-11-03 | ICC | WR | 1 | 3rd workbook version (redaction)
|  | 2021-11-04 | ICC | WR | 0.4 | 3rd workbook version (redaction)
|  | 2021-11-04 | ICC | PC | 0.4 | Current code analysis
|  | 2021-11-04 | OS | PC | 1 | Current code analysis
|  | 2021-11-04 | LB | PC | 1 | Current code analysis
|  | 2021-11-04 | CM | PC | 1 | Current code analysis
|  | 2021-11-04 | PDM | PC | 1 | Current code analysis
|  | 2021-11-05 | CM | WR | 1 | Workbook diagrams and redaction
|  | 2021-11-05 | LB | PT | 0.3 | Project tracking redaction
|  | 2021-11-05 | ICC | PT | 0.1 | Project tracking reporting
|  | 2021-11-05 | OS | PT | 0.1 | Project tracking reporting
|  | 2021-11-05 | PDM | PT | 0.1 | Project tracking reporting
|  | 2021-11-05 | CM | PT | 0.1 | Project tracking reporting
|  | 2021-11-09 | ICC | WR | 0.3 | Workbook v3 redaction
|  | 2021-11-10 | LB | GM.MET | 0.2 | Metting with M. Oudot
|  | 2021-11-10 | ICC | GM.MET | 0.2 | Sick
|  | 2021-11-10 | OS | GM.MET | 0.2 | Metting with M. Oudot
|  | 2021-11-10 | PDM | GM.MET | 0.2 | Metting with M. Oudot
|  | 2021-11-10 | CM | GM.MET | 0.2 | Metting with M. Oudot
|  | 2021-11-10 | LB | GM.MET | 0.5 | Metting to determine tasks to do
|  | 2021-11-10 | ICC | GM.MET | 0.4 | Metting to determine tasks to do
|  | 2021-11-10 | OS | GM.MET | 0.4 | Metting to determine tasks to do
|  | 2021-11-10 | PDM | GM.MET | 0.4 | Metting to determine tasks to do
|  | 2021-11-10 | CM | GM.MET | 0.4 | Metting to determine tasks to do
|  | 2021-11-10 | OS | DEV | 0.8 | Developement and creation of a Laravel project
|  | 2021-11-10 | OS | DEV.MET | 0.3 | Developement metting
|  | 2021-11-10 | CM | DEV.MET | 0.3 | Developement metting
|  | 2021-11-10 | LB | WR | 0.8 | Occupied by IRL complications
|  | 2021-11-10 | PDM | L.DB | 0.9 | Searching about GEDCOM files
|  | 2021-11-10 | CM | WR | 0.4 | Workbook v3 redaction
|  | 2021-11-10 | ICC | WR | 0.4 | Workbook v3 redaction
|  | 2021-11-11 | OS | DEV.MET | 0.3 | Developement metting
|  | 2021-11-11 | CM | DEV.MET | 0.3 | Developement metting
|  | 2021-11-11 | LB | WR | 1 | Workbook v3 redaction
|  | 2021-11-11 | CM | WR | 0.9 | Workbook v3 redaction
|  | 2021-11-11 | ICC | WR | 1 | Workbook v3 redaction
|  | 2021-11-11 | OS | DEV | 0.5 | Developement and creation of a Laravel project
|  | 2021-11-11 | PDM | L.GF | 1 | Searching about GEDCOM files
|  | 2021-11-11 | ICC | PT | 0.2 | Project tracking redaction
|  | 2021-11-17 | ICC | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-17 | CM | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-17 | LB | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-17 | OS | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-17 | PDM | GM.MET | 0.3 | Sick
|  | 2021-11-17 | ICC | DEV.MET | 0.7 | Metting for having everyone up-do-date on current code + progress
|  | 2021-11-17 | CM | DEV.MET | 0.7 | Metting for having everyone up-do-date on current code + progress
|  | 2021-11-17 | LB | DEV.MET | 0.7 | Metting for having everyone up-do-date on current code + progress
|  | 2021-11-17 | OS | DEV.MET | 0.7 | Metting for having everyone up-do-date on current code + progress
|  | 2021-11-17 | PDM | DEV.MET | 0.7 | Sick
|  | 2021-11-18 | CM | WR | 0.5 | Workbook v4 redaction
|  | 2021-11-18 | LB | WR | 0.5 | Workbook v4 redaction
|  | 2021-11-18 | ICC | DEV | 0.5 | Working on laravel + family365/laravel deployement
|  | 2021-11-18 | OS | DEV | 0.5 | Working on laravel + family365/laravel deployement
|  | 2021-11-18 | PDM | O | 1 | Medical mettings
|  | 2021-11-19 | CM | WR | 1 | Workbook v4 redaction
|  | 2021-11-19 | LB | WR | 1 | Workbook v4 redaction
|  | 2021-11-19 | ICC | DEV | 0.8 | Working on laravel + family365/laravel deployement
|  | 2021-11-19 | OS | DEV | 1 | Working on laravel + family365/laravel deployement
|  | 2021-11-19 | ICC | PT | 0.1 | Project tracking reporting
|  | 2021-11-19 | ICC | WR | 0.1 | Workbook v4 corrections
|  | 2021-11-19 | PDM | O | 0.5 | Medical mettings
|  | 2021-11-24 | ICC | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-24 | LB | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-24 | CM | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-24 | PDM | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-24 | OS | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-11-24 | ICC | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-11-24 | LB | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-11-24 | CM | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-11-24 | PDM | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-11-24 | OS | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-11-25 | LB | WR | 1 | Workbook redaction
|  | 2021-11-25 | CM | WR | 1 | Workbook redaction
|  | 2021-11-25 | PDM | WR | 1 | Workbook redaction
|  | 2021-11-25 | OS | WR | 1 | Workbook redaction
|  | 2021-11-25 | ICC | DEV | 0.5 | Laravel development
|  | 2021-11-26 | CM | DEV | 0.5 | Laravel development
|  | 2021-11-26 | PDM | DEV | 0.5 | Laravel development
|  | 2021-11-26 | OS | DEV | 0.5 | Laravel development
|  | 2021-11-26 | LB | DEV | 0.3 | Laravel development
|  | 2021-11-26 | ICC | WR | 0.8 | Workbook redaction finalisation
|  | 2021-11-26 | ICC | PT | 0.2 | Project tracking reporting
|  | 2021-11-26 | LB | PT | 0.2 | Description on how to do project tracking by ICC
|  | 2021-11-28 | ICC | DEV | 0.5 | Laravel development
|  | 2021-11-28 | CM | DEV | 0.5 | Laravel development
|  | 2021-11-28 | PDM | DEV | 0.5 | Laravel development
|  | 2021-11-28 | OS | DEV | 0.5 | Laravel development
|  | 2021-11-28 | LB | DEV | 0.4 | Laravel development
|  | 2021-12-01 | ICC | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-12-01 | LB | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-12-01 | CM | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-12-01 | PDM | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-12-01 | OS | DEV | 0.7 | Update the team on laravel project + development
|  | 2021-12-03 | CM | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-12-03 | ICC | GM.MET | 0.3 | Occupied by IRL complications
|  | 2021-12-03 | LB | GM.MET | 0.3 | Working IRL
|  | 2021-12-03 | PDM | GM.MET | 0.3 | Occupied by intership applications
|  | 2021-12-03 | OS | GM.MET | 0.3 | Occupied by intership applications
|  | 2021-12-05 | LB | WR | 1 | Workbook redaction
|  | 2021-12-05 | CM | WR | 1 | Workbook redaction
|  | 2021-12-05 | PDM | WR | 1 | Workbook redaction
|  | 2021-12-05 | OS | WR | 1 | Workbook redaction
|  | 2021-12-05 | ICC | O | 0.9 | Occupied by urgent projects
|  | 2021-12-05 | LB | PT | 0.1 | Project Tracking
|  | 2021-12-05 | ICC | PT | 0.1 | Project Tracking finishing touches
|  | 2021-12-06 | ICC | DEV | 0.5 | Laravel development
|  | 2021-12-06 | CM | DEV | 0.5 | Laravel development
|  | 2021-12-06 | PDM | DEV | 0.5 | Laravel development
|  | 2021-12-06 | OS | DEV | 0.5 | Laravel development
|  | 2021-12-06 | LB | DEV | 0.5 | Laravel development
|  | 2021-12-07 | CM | GM.MET | 0.3 | Working on laravel + family365/laravel deployement
|  | 2021-12-07 | LB | GM.MET | 0.4 | Working on laravel + family365/laravel deployement
|  | 2021-12-07 | ICC | GM.MET | 0.4 | Working on laravel + family365/laravel deployement
|  | 2021-12-07 | PDM | GM.MET | 0.4 | Working on laravel + family365/laravel deployement
|  | 2021-12-07 | OS | GM.MET | 0.4 | Working on laravel + family365/laravel deployement
|  | 2021-12-08 | CM | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-12-08 | LB | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-12-08 | ICC | GM.MET | 0.3 | Metting with M. Oudot
|  | 2021-12-08 | PDM | GM.MET | 0.3 | Working on company
|  | 2021-12-08 | OS | GM.MET | 0.3 | Sick
|  | 2021-12-08 | CM | SP | 0.3 | Fixing local server problems
|  | 2021-12-08 | ICC | SP | 0.3 | Fixing local server problems
|  | 2021-12-08 | PDM | SP | 0.3 | Fixing local server problems
|  | 2021-12-08 | OS | SP | 0.3 | Fixing local server problems
|  | 2021-12-08 | LB | SP | 0.3 | Fixing local server problems
|  | 2021-12-09 | CM | WR | 1 | Workbook redaction
|  | 2021-12-09 | LB | WR | 1 | Workbook redaction
|  | 2021-12-09 | ICC | WR | 1 | Workbook redaction
|  | 2021-12-09 | PDM | WR | 1 | Workbook redaction
|  | 2021-12-09 | OS | WR | 1 | Workbook redaction
|  | 2021-12-09 | LB | PT | 0.1 | Project Tracking
|  | 2021-12-10 | ICC | DEV | 1 | Developement of Birth page
|  | 2021-12-10 | OS | DEV | 1 | Developement of Birth page
|  | 2021-12-10 | PDM | DEV | 1 | Developement of User Management pages
|  | 2021-12-10 | LB | DEV | 1 | Developement of User Management pages
|  | 2021-12-11 | CM | DEV | 1 | Developement of Birth page
|  | 2021-12-12 | ICC | DEV | 1 | Developement of Birth page
|  | 2021-12-12 | OS | DEV | 1 | Developement of Authentification page
|  | 2021-12-12 | PDM | DEV | 1 | Developement of User Management pages
|  | 2021-12-12 | LB | DEV | 1 | Developement of User Management pages
|  | 2021-12-12 | CM | DEV | 1 | Developement of Birth page
|  | 2021-12-15 | ICC | GM.MET | 0.1 | Metting with M. Oudot
|  | 2021-12-15 | OS | GM.MET | 0.1 | Metting with M. Oudot
|  | 2021-12-15 | PDM | O | 0.1 | Sick
|  | 2021-12-15 | LB | GM.MET | 0.1 | Metting with M. Oudot
|  | 2021-12-15 | CM | GM.MET | 0.1 | Metting with M. Oudot
|  | 2021-12-16 | CM | WR | 0.4 | Workbook redaction
|  | 2021-12-16 | ICC | WR | 0.3 | Workbook redaction
|  | 2021-12-17 | OS | DEV | 0.4 | Developement of Authentification page
|  | 2021-12-17 | PDM | DEV | 0.4 | Developement of User Management pages
|  | 2021-12-17 | LB | DEV | 0.4 | Developement of User Management pages
|  | 2021-12-17 | ICC | PT | 0.1 | Project Tracking

## Report
Date | (Multiple Items)
Sum of Cost (d) | Who
What | CM | ICC | LB | OS | PDM | Grand Total
GM.MET | 0.1 | 0.1 | 0.1 | 0.1 |  | 0.4
PT |  | 0.1 |  |  |  | 0.1
WR | 0.4 | 0.3 |  |  |  | 0.7
DEV | 2 | 2 | 2.4 | 2.4 | 2.4 | 11.2
O |  |  |  |  | 0.1 | 0.1
Grand Total | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 12.5